## Implementation Backlog
Story ID | Epic | Epic Name | Story | Priority | Status | Owner | Workstream | Dependencies | Build / Deliverable | Acceptance Criteria | Canonical Source | Release Gate | Progress % | Ready? | Blocker / Decision | Sprint | Notes
E0-S1 | E0 | Foundation & Contract | Monorepo/services/modules skeleton | P0 | Not Started | Tech Lead | Backend/Architecture | None | formation, reasoning, question, growth, measurement, community 모듈 경계 구성 | 모듈 경계가 repo에서 명확히 보임 | S0-04B; S0-05B; DGM Handoff 1.1 | G-VS-01; G-VS-02 | 0% | No
E0-S2 | E0 | Foundation & Contract | PostgreSQL migration baseline | P0 | Not Started | Data Architect | DB | E0-S1 | S0-04B 핵심 table migration 작성 | Clean DB에서 migration 성공 | S0-04B | G-VS-02 | 0% | No
E0-S3 | E0 | Foundation & Contract | OpenAPI /api/v1 skeleton | P0 | Not Started | API Lead | API | E0-S1 | 공통 auth/error/version schema와 endpoint skeleton | OpenAPI lint/validation PASS | S0-05B | G-VS-03 | 0% | No
E0-S4 | E0 | Foundation & Contract | VersionLineage component | P0 | Not Started | Backend Lead | Backend/DB | E0-S2 | policy/calculation/model/prompt 등 version lineage 공통 component | Derived object가 해당 version 저장 가능 | S0-04B; S0-05B | G-VS-02; G-VS-03 | 0% | No
E0-S5 | E0 | Foundation & Contract | Request/Audit plumbing | P0 | Not Started | Security Lead | Backend/Security | E0-S3 | request_id 전파 및 민감 read/write audit 기반 | 민감 operation audit 가능; raw journal 로그 금지 | S0-05B | G-VS-03; G-VS-08 | 0% | No
E0-S6 | E0 | Foundation & Contract | CI contract gate | P0 | Not Started | QA Lead | DevOps/QA | E0-S2; E0-S3 | migration/schema/unit/contract test CI gate | 실패 시 merge 차단 | DGM-08; GM-TEST | G-VS-02; G-VS-03 | 0% | No
E1-S1 | E1 | Identity · Consent · Access | /me + tenant membership | P0 | Not Started | Backend Lead | Backend/API | E0-S3 | actor/profile/role/tenant membership 구현 | client tenant_id만으로 권한 결정하지 않음 | S0-04B; S0-05B | G-VS-08 | 0% | No
E1-S2 | E1 | Identity · Consent · Access | Versioned consent | P0 | Not Started | Privacy Lead | Backend/API | E1-S1 | consent version/effective_at/withdrawal | 철회 lineage 보존 | DGM-05; S0-05B | G-VS-08 | 0% | No
E1-S3 | E1 | Identity · Consent · Access | AccessGrant | P0 | Not Started | Privacy Lead | Backend/API | E1-S2 | resource/scope별 grant/revoke | grant 범위 밖 read DENY | DGM-05; S0-05B | G-VS-08 | 0% | No
E1-S4 | E1 | Identity · Consent · Access | Coach assignment | P0 | Not Started | Backend Lead | Backend/DB | E1-S1 | Coach assignment lifecycle | assignment만으로 private read 불가 | DGM-05 | G-VS-08 | 0% | No
E1-S5 | E1 | Identity · Consent · Access | Dual Gate policy | P0 | Not Started | Security Lead | Security/API | E1-S3; E1-S4 | assignment + active grant/consent authorization | 둘 중 하나라도 부족하면 403 | DGM-05; S0-05B | G-VS-08 | 0% | No
E1-S6 | E1 | Identity · Consent · Access | Revocation enforcement | P0 | Not Started | Security Lead | Security/API | E1-S5 | 철회 이후 protected access 차단 | future protected access DENY | DGM-05; GM-TEST | G-VS-08 | 0% | No
E1-S7 | E1 | Identity · Consent · Access | RLS defense-in-depth | P1 | Not Started | Data Architect | DB/Security | E1-S1 | tenant/private boundary RLS 보조 | server auth 우회 시에도 boundary 보조 | S0-04B | G-VS-08 | 0% | No
E2-S1 | E2 | Formation · Life Diary | Formation session | P0 | Not Started | Backend Lead | Backend/API | E1-S1 | 세션 start/close | 세션 lifecycle 추적 | S0-04B; S0-05B | G-VS-04 | 0% | No
E2-S2 | E2 | Formation · Life Diary | LifeEvent | P0 | Not Started | Backend Lead | Backend/API | E2-S1 | LifeEvent + event_time_precision | Person identity와 Episode 분리 | S0-04B | G-VS-04 | 0% | No
E2-S3 | E2 | Formation · Life Diary | Structured reflection | P0 | Not Started | Product Lead | Frontend/Backend | E2-S2 | old-person/within/responsibility/cross/kingdom 구조화 | 구조화 성찰 저장/조회 | Digital MVP Data; S0-04B | G-VS-04 | 0% | No
E2-S4 | E2 | Formation · Life Diary | LifeJournal 7 questions | P0 | Not Started | Product Lead | Frontend/Backend | E2-S3 | 7문항별 상태와 structured answer | 문항별 저장 및 재개 가능 | Digital MVP Data | G-VS-04 | 0% | No
E2-S5 | E2 | Formation · Life Diary | Raw resource separation | P0 | Not Started | Privacy Lead | DB/Security | E2-S4 | raw text/audio/transcript를 restricted ref로 분리 | Core row inline raw 금지 | DGM-05; S0-04B | G-VS-08 | 0% | No
E2-S6 | E2 | Formation · Life Diary | GrowthEpisode adapter | P0 | Not Started | Backend Lead | Backend/DB | E2-S2; E2-S4 | LifeEvent/LifeJournal source → episode_source | source lineage 추적 | S0-04B | G-VS-04 | 0% | No
E2-S7 | E2 | Formation · Life Diary | Third-party minimization | P0 | Not Started | Privacy Lead | Schema/UX | E2-S3 | 타인 관련 필드 최소화 | other_person_profile 없음 | S0-05B; DGM-05 | G-VS-08 | 0% | No
E3-S1 | E3 | AI Reasoning · Question Routing | ReasoningEpisode | P0 | Not Started | AI Lead | AI/Backend | E2-S6 | episode/context/version 연결 reasoning root | Reasoning lineage 저장 | MVP AI Reasoning; S0-04B | G-VS-05 | 0% | No
E3-S2 | E3 | AI Reasoning · Question Routing | Minimal Context Snapshot | P0 | Not Started | AI Lead | AI/Privacy | E3-S1 | structured minimal context snapshot | raw 무제한 context 저장 금지 | MVP AI Reasoning; DGM-05 | G-VS-05; G-VS-08 | 0% | No
E3-S3 | E3 | AI Reasoning · Question Routing | RS transition | P0 | Not Started | AI Lead | AI/Backend | E3-S1 | RS-00~RS-10 transition lineage | state transition 재현 가능 | MVP AI Reasoning | G-VS-05 | 0% | No
E3-S4 | E3 | AI Reasoning · Question Routing | Question registry | P0 | Not Started | AI Lead | AI/Data | E0-S4 | question_id/version/registry/ontology version | 질문 version immutable lineage | DGM-03 | G-VS-05 | 0% | No
E3-S5 | E3 | AI Reasoning · Question Routing | Routing decision | P0 | Not Started | AI Lead | AI/Backend | E3-S2; E3-S4 | 질문 선택 이유와 routing decision 저장 | routing reason 추적 | DGM-03; S0-05B | G-VS-05 | 0% | No
E3-S6 | E3 | AI Reasoning · Question Routing | Question instance/response | P0 | Not Started | Frontend Lead | Frontend/API | E3-S5 | 1~3 질문 + answer states | ANSWERED/SKIPPED/DECLINED/ABANDONED 보존 | DGM-03 | G-VS-05 | 0% | No
E3-S7 | E3 | AI Reasoning · Question Routing | Stop/Handoff | P0 | Not Started | AI Lead | AI/Safety | E3-S3 | AI stop/human handoff state | 중단/인계 lineage | MVP AI Reasoning; S0-05B | G-VS-05; G-VS-11 | 0% | No
E3-S8 | E3 | AI Reasoning · Question Routing | AI boundary | P0 | Not Started | AI Lead | AI/QA | E3-S6 | 금지된 단일 영성판정 output guard | 영적 수준/성령 점수/옛사람 점수 반환 없음 | S0-05B; GM-TEST | G-VS-05 | 0% | No
E4-S1 | E4 | Candidate · Confirmation · Evidence | SignalCandidate | P0 | Not Started | Measurement Lead | Backend/AI | E3-S6 | candidate + provenance | model/prompt/registry lineage 저장 | DGM-01; S0-04B | G-VS-06 | 0% | No
E4-S2 | E4 | Candidate · Confirmation · Evidence | HumanConfirmation | P0 | Not Started | Measurement Lead | Frontend/Backend | E4-S1 | CONFIRMED/PARTIAL/UNCERTAIN/REJECTED | 사람 확인 상태 보존 | DGM-01; S0-05B | G-VS-06 | 0% | No
E4-S3 | E4 | Candidate · Confirmation · Evidence | Correction lineage | P0 | Not Started | Measurement Lead | Backend/DB | E4-S2 | corrected_signal_id/meaning | 수정 전후 lineage 보존 | DGM-01 | G-VS-06 | 0% | No
E4-S4 | E4 | Candidate · Confirmation · Evidence | Evidence gate | P0 | Not Started | Backend Lead | Backend/QA | E4-S2 | eligible evidence creation policy | UNCERTAIN/REJECTED → eligible evidence 0 | GM-TEST; S0-05B | G-VS-06 | 0% | No
E4-S5 | E4 | Candidate · Confirmation · Evidence | PARTIAL policy | P0 | Blocked | Measurement Lead | Policy/Backend | E4-S2 | PARTIAL eligibility policy-driven | hardcode 금지; policy_version 필수 | DGM-01; GM-DICT | G-VS-06 | 0% | No
E4-S6 | E4 | Candidate · Confirmation · Evidence | Rerun safety | P0 | Not Started | AI Lead | AI/Backend | E4-S2 | AI rerun과 human decision 분리 | 기존 confirmation overwrite 금지 | S0-04B | G-VS-06 | 0% | No
E4-S7 | E4 | Candidate · Confirmation · Evidence | No spiritual total | P0 | Not Started | QA Lead | Schema/API/UX | E4-S4 | 금지 필드/route 검증 | GS 합산 총점/개인순위 없음 | GM-TEST; S0-05B | G-VS-06 | 0% | No
E5-S1 | E5 | Practice · Outcome | Practice state | P0 | Not Started | Backend Lead | Backend/API | E4-S4 | NONE/ATTEMPTED/COMPLETED/UNKNOWN | 상태 저장/전이 | S0-04B; S0-05B | G-VS-07 | 0% | No
E5-S2 | E5 | Practice · Outcome | Opportunity state | P0 | Not Started | Measurement Lead | Backend/DB | E5-S1 | YES/NO/UNSURE/UNKNOWN 별도 | Outcome와 별도 저장 | GM-DICT | G-VS-07 | 0% | No
E5-S3 | E5 | Practice · Outcome | Outcome direction | P0 | Not Started | Backend Lead | Backend/API | E5-S1 | IMPROVED/UNCHANGED/WORSENED/MIXED/UNKNOWN/NO_OPPORTUNITY | typed outcome 보존 | GM-DICT; S0-05B | G-VS-07 | 0% | No
E5-S4 | E5 | Practice · Outcome | Repair subtype | P1 | Not Started | Measurement Lead | Backend/DB | E5-S3 | 용서/사과/관계수선/건강한 경계 subtype | direction과 분리 | GM-DICT | G-VS-07 | 0% | No
E5-S5 | E5 | Practice · Outcome | Practice≠Outcome invariant | P0 | Not Started | QA Lead | QA/Backend | E5-S3 | COMPLETED가 IMPROVED 자동생성하지 않음 | contract test PASS | GM-TEST | G-VS-07 | 0% | No
E5-S6 | E5 | Practice · Outcome | No Opportunity≠Failure | P0 | Not Started | QA Lead | QA/Measurement | E5-S2; E5-S3 | NO_OPPORTUNITY failure count 제외 | contract test PASS | GM-TEST | G-VS-07 | 0% | No
E6-S1 | E6 | Survey · Dynamics · Personal Profile | Instrument/item version | P0 | Not Started | Measurement Lead | DB/API | E0-S4 | administration 당시 immutable version | version lineage 보존 | GM-SUR; S0-04B | G-VS-07 | 0% | No
E6-S2 | E6 | Survey · Dynamics · Personal Profile | Response state | P0 | Not Started | Measurement Lead | Frontend/Backend | E6-S1 | ANSWERED/MISSING/DECLINED/NOT_SHARED/NOT_OBSERVABLE/UNKNOWN/NA | 상태 손실 없음 | GM-SUR; GM-DICT | G-VS-07 | 0% | No
E6-S3 | E6 | Survey · Dynamics · Personal Profile | Missing≠0 | P0 | Not Started | QA Lead | QA/Measurement | E6-S2 | 비응답 numeric zero coercion 차단 | contract test PASS | GM-TEST | G-VS-07 | 0% | No
E6-S4 | E6 | Survey · Dynamics · Personal Profile | Dynamics recompute | P0 | Not Started | Data Lead | Backend/Data | E4-S4; E5-S3; E6-S2 | deterministic calculation_version | same input+versions 재현 | DGM-02; GM-DICT | G-VS-07; G-VS-10 | 0% | No
E6-S5 | E6 | Survey · Dynamics · Personal Profile | Personal profile | P0 | Not Started | Frontend Lead | Frontend/API | E6-S4 | typed states + coverage + limitations | 총점 없이 시간축 Profile | DGM-02; S0-05B | G-VS-07 | 0% | No
E6-S6 | E6 | Survey · Dynamics · Personal Profile | No ranking | P0 | Not Started | QA Lead | QA/UX | E6-S5 | 금지 score/rank UI/API scan | overall spiritual score/peer rank 없음 | GM-TEST | G-VS-07 | 0% | No
E6-S7 | E6 | Survey · Dynamics · Personal Profile | Provisional thresholds | P1 | Blocked | Measurement Lead | Policy/Data | E6-S4 | 미검증 cutoff registry/config | code enum에 freeze 금지 | DGM-02; GM-VAL | G-VS-07 | 0% | No
E7-S1 | E7 | Coach Surface | Assignment list | P0 | Not Started | Frontend Lead | Frontend/API | E1-S4 | /coach/assignments 최소 목록 | 할당된 participant만 | S0-05B | G-VS-08 | 0% | No
E7-S2 | E7 | Coach Surface | Approved participant brief | P0 | Not Started | Frontend Lead | Frontend/API | E1-S5; E4-S4 | scope-limited episode/evidence read | Dual Gate 실패 시 403 | DGM-05; S0-05B | G-VS-08 | 0% | No
E7-S3 | E7 | Coach Surface | Confirmation action | P0 | Not Started | Backend Lead | Frontend/API | E7-S2 | Coach human confirmation | 승인 scope 내에서만 | S0-05B | G-VS-06; G-VS-08 | 0% | No
E7-S4 | E7 | Coach Surface | Handoff inbox | P0 | Not Started | Frontend Lead | Frontend/API | E3-S7; E7-S2 | handoff accept workflow | AI handoff lineage 연결 | S0-05B | G-VS-05; G-VS-08 | 0% | No
E7-S5 | E7 | Coach Surface | Privacy cue | P1 | Not Started | UX Lead | Frontend/UX | E7-S2 | 공유 범위/근거 UI 표시 | Coach가 권한을 추정하지 않음 | DGM-05 | G-VS-08 | 0% | No
E8-S1 | E8 | Community · Pastor-safe | Aggregation worker | P0 | Not Started | Data Lead | Backend/Data | E6-S4 | eligible structured data만 집계 | raw/personal narrative 미사용 | GM-AGG; GM-COM | G-VS-09 | 0% | No
E8-S2 | E8 | Community · Pastor-safe | Minimum cohort policy | P0 | Blocked | Privacy Lead | Policy/Data | E8-S1 | threshold 미달 suppression | 미달을 0으로 표시하지 않음 | GM-AGG; DGM-05 | G-VS-09 | 0% | No
E8-S3 | E8 | Community · Pastor-safe | Secondary suppression | P0 | Not Started | Privacy Lead | Data/Security | E8-S2 | difference attack 보호 | 희소 cell 역산 차단 | GM-AGG; GM-TEST | G-VS-09 | 0% | No
E8-S4 | E8 | Community · Pastor-safe | Community Profile | P0 | Not Started | Data Lead | Backend/API | E8-S1; E8-S3 | typed state+coverage+limitations+versions | aggregate profile 재현 가능 | GM-COM; S0-05B | G-VS-09 | 0% | No
E8-S5 | E8 | Community · Pastor-safe | Pastor API | P0 | Not Started | API Lead | API | E8-S4 | aggregate-only read model | 개인 resource 조회 후 후처리 금지 | S0-05B; DGM-05 | G-VS-09 | 0% | No
E8-S6 | E8 | Community · Pastor-safe | No reverse link | P0 | Not Started | QA Lead | QA/API | E8-S5 | response privacy assertion | user_id/token/episode_id/raw_text 없음 | GM-TEST | G-VS-09 | 0% | No
E8-S7 | E8 | Community · Pastor-safe | No church score | P0 | Not Started | QA Lead | QA/UX | E8-S5 | 금지 score/list scan | Church Spiritual Score/non-responder list 없음 | GM-TEST | G-VS-09 | 0% | No
E9-S1 | E9 | Safety · Audit · Privacy | Safety event | P0 | Not Started | Safety Lead | Backend/Safety | E3-S3 | critical safety state | growth routing보다 우선 | S0-05B | G-VS-11 | 0% | No
E9-S2 | E9 | Safety · Audit · Privacy | AI stop/handoff override | P0 | Not Started | Safety Lead | AI/Safety | E3-S7; E9-S1 | unresolved safety에서 normal flow stop | override test PASS | GM-TEST | G-VS-11 | 0% | No
E9-S3 | E9 | Safety · Audit · Privacy | Audit event | P0 | Not Started | Security Lead | Security/Backend | E0-S5 | 민감 read/write/export/override audit | raw journal 미기록 | S0-05B | G-VS-08; G-VS-11 | 0% | No
E9-S4 | E9 | Safety · Audit · Privacy | Break-glass | P1 | Not Started | Security Lead | Security | E9-S3 | 별도 scope/justification/start/end | 일반 admin token과 분리 | S0-05B | G-VS-11 | 0% | No
E9-S5 | E9 | Safety · Audit · Privacy | Raw deletion lineage | P0 | Not Started | Privacy Lead | Privacy/Data | E2-S5 | raw 삭제와 파생 index/vector 제거 추적 | deletion lineage audit 가능 | DGM-05 | G-VS-08 | 0% | No
E9-S6 | E9 | Safety · Audit · Privacy | Pastor privacy architecture | P0 | Not Started | Data Architect | Data/Security | E8-S5 | aggregate query architecture | 개인 row 조회 후 masking 금지 | GM-AGG | G-VS-09 | 0% | No
E9-S7 | E9 | Safety · Audit · Privacy | Research isolation | P1 | Not Started | Research Lead | API/Security | E9-S3 | pseudonymized dataset route | production personal API direct use 금지 | DGM-07; S0-05B | G-VS-08 | 0% | No
E10-S1 | E10 | Synthetic Regression | Fixture seed loader | P0 | Not Started | QA Lead | QA/Data | E6-S4; E8-S4 | GM-TEST-FIX-DATA seed | 30 synthetic patterns 로드 | GM-TEST-FIX-DATA-01 | G-VS-10 | 0% | No
E10-S2 | E10 | Synthetic Regression | P0 invariant automation | P0 | Not Started | QA Lead | QA | E10-S1 | Candidate/Missing/Opportunity/Practice/Pastor/Safety assertions | P0 assertions PASS | GM-TEST-01 | G-VS-10 | 0% | No
E10-S3 | E10 | Synthetic Regression | Authorization adversarial suite | P0 | Not Started | Security Lead | QA/Security | E10-S1 | Dual Gate/revocation/suppression/difference attack | adversarial tests PASS | GM-TEST-FIX-01 | G-VS-08; G-VS-09; G-VS-10 | 0% | No
E10-S4 | E10 | Synthetic Regression | Version recompute regression | P0 | Not Started | Data Lead | QA/Data | E10-S1 | same input/version deterministic recompute | expected result 일치 | GM-TEST-FIX-DATA-01 | G-VS-10 | 0% | No
E11-S1 | E11 | S30 Dry Run | Participant dry run | P0 | Not Started | Product Lead | Ops/UX | E10-S2 | T0/W4/W8/W12 + event/confirmation/action flow rehearsal | 운영 막힘 없이 완주 | S30 Runbook; GM-S30-PACK | G-VS-12 | 0% | No
E11-S2 | E11 | S30 Dry Run | Coach dry run | P0 | Not Started | Coach Ops Lead | Ops/UX | E10-S3 | assignment/grant/brief/confirmation/handoff rehearsal | Dual Gate 유지하며 운영 가능 | S30 Runbook | G-VS-12 | 0% | No
E11-S3 | E11 | S30 Dry Run | Pastor dry run | P0 | Not Started | Product Lead | Ops/UX | E10-S3 | aggregate profile/suppression/data quality rehearsal | 개인 역추적 불가 | S30 Runbook | G-VS-12 | 0% | No
E11-S4 | E11 | S30 Dry Run | Research export rehearsal | P1 | Not Started | Research Lead | Research/Data | E10-S4 | pseudonymized structured export | raw journal 없음 | DGM-07 | G-VS-12 | 0% | No
E11-S5 | E11 | S30 Dry Run | DGM-08 release decision | P0 | Not Started | Governance Lead | Governance/QA | E11-S1; E11-S2; E11-S3 | GO/REVISE/STOP evidence review | decision + unresolved issues 기록 | DGM-08 | G-VS-12 | 0% | No

## Dashboard
CHGO Implementation Backlog 1.1 — MVP Vertical Slice Dashboard
KPI | Value | Epic | Name | Stories | Done | Progress
Total Stories | 76 | E0 | Foundation & Contract | 6 | 0 | 0%
P0 Stories | 69 | E1 | Identity · Consent · Access | 7 | 0 | 0%
Done | 0 | E2 | Formation · Life Diary | 7 | 0 | 0%
In Progress | 0 | E3 | AI Reasoning · Question Routing | 8 | 0 | 0%
Blocked | 3 | E4 | Candidate · Confirmation · Evidence | 7 | 0 | 0%
Overall Progress | 0% | E5 | Practice · Outcome | 6 | 0 | 0%
|  | E6 | Survey · Dynamics · Personal Profile | 7 | 0 | 0%
|  | E7 | Coach Surface | 5 | 0 | 0%
|  | E8 | Community · Pastor-safe | 7 | 0 | 0%
|  | E9 | Safety · Audit · Privacy | 7 | 0 | 0%
|  | E10 | Synthetic Regression | 4 | 0 | 0%
|  | E11 | S30 Dry Run | 5 | 0 | 0%

## Release Gates
Gate | Name | PASS Condition | Status | Owner | Evidence / Notes
G-VS-01 | Canonical | S0-01~05B Active sources frozen | Not Started | Governance Lead
G-VS-02 | Data | Core migrations repeatable | Not Started | Data Architect
G-VS-03 | API | OpenAPI validates; auth/error schemas implemented | Not Started | API Lead
G-VS-04 | Formation | LifeEvent→Reflection→Episode works | Not Started | Product/Backend
G-VS-05 | AI | Reasoning→Question with stop/handoff works | Not Started | AI Lead
G-VS-06 | Growth | Candidate→Human Confirmation→Evidence works | Not Started | Measurement Lead
G-VS-07 | Measurement | Practice/Outcome/Survey/Dynamics invariants pass | Not Started | Measurement/QA
G-VS-08 | Privacy | Dual Gate/revocation/raw separation pass | Not Started | Privacy/Security
G-VS-09 | Community | Pastor aggregate-only + suppression pass | Not Started | Data/Privacy
G-VS-10 | Synthetic | GM-TEST-FIX-DATA critical assertions pass | Not Started | QA Lead
G-VS-11 | Safety | critical override pass | Not Started | Safety Lead
G-VS-12 | Governance | DGM-08 GO or documented REVISE | Not Started | Governance Lead

## Source Map
Priority | Source | Role in Implementation | Active Use
P0 | S0-00 / S0-00A Registry | Active/Reference/Superseded 상태 판정 | Governance
P0 | S0-01 Boundary Constitution | JesusLife↔CHGO 경계 | All
P0 | S0-02 Canonical Scope & Meaning Freeze | JesusLife 의미 Freeze | All
P0 | S0-03 Ecclesiology Extension | 교회론 Extension 경계 | Community
P0 | S0-04B Integrated Core ERD v1.0 | 전체 저장 구조 Source of Truth | DB
P0 | S0-05B Integrated API/OpenAPI v1.0 | 전체 읽기/쓰기/권한 Source of Truth | API/Security
P1 | DGM-01~08 | Signal/Dynamics/Question/Journey/Privacy/UI/Research/Release 세부 계약 | Domain
P1 | GM-DICT / TRACE / ALIGN / TEST | 측정 의미·추적·구현·검증 | Measurement/QA
P1 | Digital JesusLife MVP Data & Event Schema | Formation 세부 Source | Formation
P1 | AI Coach Reasoning & Prompt Architecture | AI Reasoning 세부 Source | AI
P1 | GM-TEST-FIX-01 / GM-TEST-FIX-DATA-01 | Synthetic regression 기준 | QA
P2 | S30 Runbook / FORM / PACK / VAL-S30 | 현장 파일럿 실행 Source | S30 Ops
REF | 90 / 99 / 과거 ERD·API | 구현 기준으로 사용하지 않음 | Reference only

## Lists
Status | Priority | Ready | Sprint
Not Started | P0 | No | S0
Ready | P1 | Yes | S1
In Progress | P2 |  | S2
Blocked |  |  | S3
In Review |  |  | S4
Done |  |  | S5
S6
S7
S8