## Church OS 2.0 Delta
Story ID | Epic | Epic Name | Story | Priority | Status | Owner | Workstream | Dependencies | Build / Deliverable | Acceptance Criteria | Canonical Source | Release Gate | Progress % | Ready? | Blocker / Decision | Sprint | Release Slice | Test IDs | Notes
C0-S1 | C0 | Handoff & Contract Freeze | Import 1.2 handoff sources | P0 | Not Started | Tech Lead | Architecture | None | CO-00~CO-12 approved snapshots in repo | Artifact versions and paths match DGM 1.2 | DGM Handoff 1.2 | CO-G01 | 0% | No |  | CS0 | Foundation | CI-01~10
C0-S2 | C0 | Handoff & Contract Freeze | DEV-002 physical diff | P0 | Not Started | Data Architect | DB | C0-S1 | Compare DEV-002 physical names to DEV-002A delta | No destructive ALTER generated from guessed names | DEV-002A Schema Delta 2.0 | CO-G02 | 0% | No | DEV-002 physical exact names | CS0 | Foundation | D2-T16
C0-S3 | C0 | Handoff & Contract Freeze | OpenAPI delta CI import | P0 | Not Started | API Lead | API | C0-S1 | Load OpenAPI 3.1 delta into validation pipeline | Parse/lint passes; forbidden bridge fields linted | Church OS OpenAPI Delta 2.0 | CO-G03 | 0% | No |  | CS0 | Foundation | API-G01~10
C0-S4 | C0 | Handoff & Contract Freeze | Church OS 2.0 CI gate | P0 | Not Started | QA Lead | DevOps/QA | C0-S2; C0-S3 | CI-01~CI-10 pipeline stages | Required blocker failure prevents release | DGM Handoff 1.2 | CO-G10 | 0% | No |  | CS0 | Foundation | CI-01~10
C0-S5 | C0 | Handoff & Contract Freeze | Open decision registry owners | P0 | Not Started | Product Lead | Governance | C0-S1 | OD-01~OD-10 owner + decision route | No OPEN item silently hard-coded | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-01~OD-10 | CS0 | Foundation
C1-S1 | C1 | Church Core · People & Groups | Tenant/campus hierarchy | P0 | Not Started | Backend Lead | Backend/DB | C0-S2 | church_tenant/campus 2.0 alignment | tenant isolation and parent hierarchy preserved | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS1 | MVP-A | D2-T11
C1-S2 | C1 | Church Core · People & Groups | People/household operational SoR | P0 | Not Started | Backend Lead | Backend/DB | C1-S1 | person/household/member records | Real identity remains L3 SoR | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS1 | MVP-A | D2-T01
C1-S3 | C1 | Church Core · People & Groups | Role assignment scope | P0 | Not Started | Security Lead | Security/API | C1-S2 | role assignment with tenant/campus scope | Client tenant value never authorizes by itself | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS1 | MVP-A | D2-T11
C1-S4 | C1 | Church Core · People & Groups | Groups membership | P0 | Not Started | Backend Lead | Backend/API | C1-S2 | group entity/membership lifecycle | Tenant-scoped membership works | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS1 | MVP-A
C1-S5 | C1 | Church Core · People & Groups | Group meeting/attendance | P0 | Not Started | Backend Lead | Backend/API | C1-S4 | meeting + attendance records | Core works without CHGO Engine | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS1 | MVP-A | IC-T13
C1-S6 | C1 | Church Core · People & Groups | Operational People Journey | P0 | Not Started | Product/Backend | Backend/API | C1-S2 | person_journey_state/event | No maturity_score/faith_level/spiritual_rank | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS1 | MVP-A | D2-T01; D2-T02
C2-S1 | C2 | Today · Worship · Events · Content | Member Today read model | P0 | Not Started | Backend Lead | Backend/API | C1-S2 | today_action_source/state | Today is read model, not duplicate SoR | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS2 | MVP-A | D2-T14; UX-A01
C2-S2 | C2 | Today · Worship · Events · Content | Today source adapters | P0 | Not Started | Backend Lead | Backend | C2-S1 | care/gathering/formation/mission/serve/update adapters | Operational sources continue if L2 unavailable | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS2 | MVP-A | API-G07
C2-S3 | C2 | Today · Worship · Events · Content | Role-aware navigation | P0 | Not Started | Frontend Lead | Frontend | C1-S3 | member/leader/pastor/admin nav config | Navigation differs by role and scope | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS2 | MVP-A | UX-A02
C2-S4 | C2 | Today · Worship · Events · Content | Worship/service flow | P0 | Not Started | Product/Backend | Frontend/Backend | C1-S2 | worship/service schedule + participation | Core operation independent of CHGO | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS2 | MVP-A | GATE-PROD-01
C2-S5 | C2 | Today · Worship · Events · Content | Events flow | P0 | Not Started | Product/Backend | Frontend/Backend | C1-S2 | event list/detail/registration state | Tenant/role boundary pass | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS2 | MVP-A | GATE-PROD-02
C2-S6 | C2 | Today · Worship · Events · Content | Communication delivery | P0 | Not Started | Backend Lead | Backend/Integration | C1-S3 | announcement/notification delivery | Sensitive preview does not duplicate protected content | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS2 | MVP-A | D2-T15
C2-S7 | C2 | Today · Worship · Events · Content | Content module | P0 | Not Started | Product Lead | Frontend/Backend | C1-S1 | content item/list/detail | Tenant ownership and publish state preserved | PRS 2.0; UXIA 2.0; DEV-002A | CO-G04 | 0% | No |  | CS2 | MVP-A
C3-S1 | C3 | Care · Prayer · Privacy | Care request visibility | P0 | Not Started | Privacy Lead | Frontend/Backend | C1-S3 | care_request visibility/sensitivity | Visibility shown before submit | PRS 2.0; UXIA 2.0; DEV-002A | CO-G05 | 0% | No |  | CS2 | MVP-A | UX-A03
C3-S2 | C3 | Care · Prayer · Privacy | Protected care note separation | P0 | Not Started | Privacy Lead | DB/Security | C3-S1 | care_protected_note restricted boundary | Pastor overview excludes protected note | PRS 2.0; UXIA 2.0; DEV-002A | CO-G05 | 0% | No |  | CS2 | MVP-A | D2-T09
C3-S3 | C3 | Care · Prayer · Privacy | Care assignment lifecycle | P0 | Not Started | Backend Lead | Backend/API | C3-S1 | care_assignment + handoff | Only assigned/authorized roles access protected scope | PRS 2.0; UXIA 2.0; DEV-002A | CO-G05 | 0% | No |  | CS2 | MVP-A | IC-G02
C3-S4 | C3 | Care · Prayer · Privacy | Prayer request visibility | P0 | Not Started | Privacy Lead | Frontend/Backend | C1-S3 | prayer_request visibility policy | Visibility/processing scope explicit | PRS 2.0; UXIA 2.0; DEV-002A | CO-G05 | 0% | No |  | CS2 | MVP-A | UX-A03
C3-S5 | C3 | Care · Prayer · Privacy | Prayer response/follow-up | P0 | Not Started | Backend Lead | Backend/API | C3-S4 | prayer_response lifecycle | No protected raw body in general audit | PRS 2.0; UXIA 2.0; DEV-002A | CO-G05 | 0% | No |  | CS2 | MVP-A | D2-T15
C3-S6 | C3 | Care · Prayer · Privacy | Sensitive access audit | P0 | Not Started | Security Lead | Security/DB | C3-S2; C3-S4 | append-oriented sensitive_access_audit | No raw sensitive text logged | PRS 2.0; UXIA 2.0; DEV-002A | CO-G05 | 0% | No |  | CS2 | MVP-A | D2-T15
C4-S1 | C4 | Formation Journey | Formation Pack registry | P0 | Not Started | Domain/Backend | Backend/DB | C1-S1 | provider-neutral formation_pack | Pack not hard-coded to JesusLife | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B
C4-S2 | C4 | Formation Journey | Journey/unit/activity model | P0 | Not Started | Backend Lead | Backend/API | C4-S1 | formation_journey/unit/activity | Versioned ordered journey works | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B
C4-S3 | C4 | Formation Journey | Enrollment/progress | P0 | Not Started | Backend Lead | Backend/API | C4-S2 | enrollment + activity_progress | Completion is process state only | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B | D2-T02
C4-S4 | C4 | Formation Journey | Structured reflection | P0 | Not Started | Product/Backend | Frontend/Backend | C4-S2; C3-S6 | formation_reflection structured derivative | Protected raw ref separated | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B | API-G03
C4-S5 | C4 | Formation Journey | Practice opportunity | P0 | Not Started | Measurement Lead | Backend/API | C4-S2 | practice_opportunity typed state | NO_OPPORTUNITY remains explicit | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B | D2-T04
C4-S6 | C4 | Formation Journey | Practice record | P0 | Not Started | Measurement Lead | Backend/API | C4-S5 | practice_record | Practice does not auto-create outcome improvement | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B | D2-T03
C4-S7 | C4 | Formation Journey | Formation UX | P0 | Not Started | Frontend Lead | Frontend | C4-S3; C4-S6 | journey/unit/practice screens | No spiritual maturity label | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B | UX-A04
C5-S1 | C5 | Mission · Serve | Mission program/run | P0 | Not Started | Backend Lead | Backend/DB | C1-S1 | mission_program + mission_run | Reusable definition separated from actual run | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B
C5-S2 | C5 | Mission · Serve | Mission enrollment | P0 | Not Started | Backend Lead | Backend/API | C5-S1 | mission_enrollment lifecycle | Opt-in/required policy represented explicitly | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B
C5-S3 | C5 | Mission · Serve | Mission action definitions | P0 | Not Started | Product/Backend | Backend/API | C5-S1 | mission_action_definition cadence | Configurable duration/cadence not theological claim | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B
C5-S4 | C5 | Mission · Serve | Mission action record | P0 | Not Started | Backend Lead | Backend/API | C5-S2; C5-S3 | mission_action_record + opportunity state | No opportunity is not failure | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B | D2-T04
C5-S5 | C5 | Mission · Serve | Mission review | P0 | Not Started | Product Lead | Frontend/Backend | C5-S4 | visibility-scoped mission_review | Private reflection not auto-shared | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B
C5-S6 | C5 | Mission · Serve | Serve opportunity/assignment | P0 | Not Started | Backend Lead | Backend/API | C1-S2 | serve_opportunity/assignment | Serving count not maturity proxy | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B | GATE-PROD-04
C5-S7 | C5 | Mission · Serve | Mission UX | P0 | Not Started | Frontend Lead | Frontend | C5-S2; C5-S4 | mission today/progress/review screens | No spiritual leaderboard | PRS 2.0; UXIA 2.0; DEV-002A | CO-G06 | 0% | No |  | CS3 | MVP-B | UX-A05
C6-S1 | C6 | Privacy Gateway · CHGO Bridge | Purpose registry | P0 | Not Started | Privacy Lead | Backend/DB | C0-S2 | purpose_registry stable codes | Protected exchange has approved purpose | Integration Contract 1.0; DEV-002A; OpenAPI Delta 2.0 | CO-G07 | 0% | No |  | CS4 | MVP-C | API-G01
C6-S2 | C6 | Privacy Gateway · CHGO Bridge | Pseudonym subject link | P0 | Not Started | Security Lead | DB/Security | C6-S1; C1-S2 | restricted pseudonym_subject_link | Pastor/leader SELECT denied; no person_id bridge payload | Integration Contract 1.0; DEV-002A; OpenAPI Delta 2.0 | CO-G07 | 0% | No |  | CS4 | MVP-C | D2-T06; API-G02
C6-S3 | C6 | Privacy Gateway · CHGO Bridge | Gateway decision pipeline | P0 | Not Started | Privacy Lead | Security/API | C6-S1; C6-S2 | ALLOW/REDACT/DENY/SUPPRESS/HANDOFF | tenant/auth/purpose/consent/scope/minimization/audit enforced | Integration Contract 1.0; DEV-002A; OpenAPI Delta 2.0 | CO-G07 | 0% | No |  | CS4 | MVP-C | IC-G02
C6-S4 | C6 | Privacy Gateway · CHGO Bridge | Event outbox | P0 | Not Started | Backend Lead | Backend/DB | C6-S3 | integration_event_outbox | Idempotent allowlisted minimized payload | Integration Contract 1.0; DEV-002A; OpenAPI Delta 2.0 | CO-G07 | 0% | No |  | CS4 | MVP-C | D2-T07
C6-S5 | C6 | Privacy Gateway · CHGO Bridge | Delivery ledger/retry | P0 | Not Started | Backend Lead | Backend/Integration | C6-S4 | delivery ledger + retry/replay | L2 failure does not rollback Church transaction | Integration Contract 1.0; DEV-002A; OpenAPI Delta 2.0 | CO-G07 | 0% | No |  | CS4 | MVP-C | D2-T08; IC-T13
C6-S6 | C6 | Privacy Gateway · CHGO Bridge | Consent revoke control | P0 | Not Started | Privacy Lead | Backend/API | C6-S3 | consent.revoked control event | Future protected enqueue/access denied | Integration Contract 1.0; DEV-002A; OpenAPI Delta 2.0 | CO-G07 | 0% | No |  | CS4 | MVP-C | D2-T12; IC-T12
C6-S7 | C6 | Privacy Gateway · CHGO Bridge | Subject deletion control | P0 | Not Started | Privacy Lead | Backend/API | C6-S3 | subject.deleted propagation | Deletion/revocation lineage auditable | Integration Contract 1.0; DEV-002A; OpenAPI Delta 2.0 | CO-G07 | 0% | No |  | CS4 | MVP-C
C6-S8 | C6 | Privacy Gateway · CHGO Bridge | Safety handoff override | P0 | Not Started | Safety Lead | Backend/Safety | C6-S3 | safety.handoff.requested | HANDOFF overrides growth flow | Integration Contract 1.0; DEV-002A; OpenAPI Delta 2.0 | CO-G07 | 0% | No |  | CS4 | MVP-C | IC-T16
C7-S1 | C7 | CHGO Response · Pastor-safe Intelligence | L2 bounded response adapter | P0 | Not Started | Backend Lead | Backend/API | C6-S5 | status/data/provenance/privacy/trace adapter | Derived result keeps ontology/model/policy/calculation lineage | Integration Contract 1.0; OpenAPI Delta 2.0; UXIA 2.0 | CO-G08 | 0% | No |  | CS5 | MVP-C | API-G10
C7-S2 | C7 | CHGO Response · Pastor-safe Intelligence | Candidate display boundary | P0 | Not Started | Growth Lead | Frontend/Backend | C7-S1 | candidate display/ref cache only | Candidate never rendered as confirmed Evidence | Integration Contract 1.0; OpenAPI Delta 2.0; UXIA 2.0 | CO-G08 | 0% | No |  | CS5 | MVP-C | API-G04; UX-A06
C7-S3 | C7 | CHGO Response · Pastor-safe Intelligence | Human confirmation command | P0 | Not Started | Growth Lead | Frontend/Backend | C7-S2 | confirm/correct/uncertain/reject flow | AI cannot auto-confirm | Integration Contract 1.0; OpenAPI Delta 2.0; UXIA 2.0 | CO-G08 | 0% | No |  | CS5 | MVP-C | IC-G03
C7-S4 | C7 | CHGO Response · Pastor-safe Intelligence | Practice/outcome response separation | P0 | Not Started | Measurement Lead | Backend/API | C7-S1 | distinct practice/outcome resources | Practice does not imply outcome | Integration Contract 1.0; OpenAPI Delta 2.0; UXIA 2.0 | CO-G08 | 0% | No |  | CS5 | MVP-C | API-G04
C7-S5 | C7 | CHGO Response · Pastor-safe Intelligence | Pastor community growth query | P0 | Not Started | Data/Privacy Lead | Backend/API | C7-S1 | aggregate-only CHGO query | No person_id/subject_key/raw reflection/evidence link | Integration Contract 1.0; OpenAPI Delta 2.0; UXIA 2.0 | CO-G08 | 0% | No |  | CS5 | MVP-C | D2-T10; API-G05
C7-S6 | C7 | CHGO Response · Pastor-safe Intelligence | Suppression/coverage state | P0 | Not Started | Data/Privacy Lead | Backend/API | C7-S5 | typed suppression + coverage | SUPPRESSED never mapped to zero/no-growth | Integration Contract 1.0; OpenAPI Delta 2.0; UXIA 2.0 | CO-G08 | 0% | No |  | CS5 | MVP-C | API-G06
C7-S7 | C7 | CHGO Response · Pastor-safe Intelligence | Pastor Community Growth UX | P0 | Not Started | Frontend Lead | Frontend | C7-S5; C7-S6 | aggregate/suppressed/provenance UI | No reverse personal drill-down | Integration Contract 1.0; OpenAPI Delta 2.0; UXIA 2.0 | CO-G08 | 0% | No |  | CS5 | MVP-C | IC-G04
C8-S1 | C8 | White-label · Headless | Tenant branding config | P1 | Not Started | Frontend/Backend | Frontend/Backend | C1-S1 | tenant_brand_config | Branding cannot alter governance policy | PRS 2.0; UXIA 2.0; DEV-002A; OpenAPI Delta 2.0 | CO-G09 | 0% | No |  | CS6 | Platform 2.0 | GATE-PROD-06
C8-S2 | C8 | White-label · Headless | Navigation config | P1 | Not Started | Frontend/Backend | Frontend/Backend | C2-S3 | tenant_navigation_config | Policy gates cannot be hidden/disabled | PRS 2.0; UXIA 2.0; DEV-002A; OpenAPI Delta 2.0 | CO-G09 | 0% | No |  | CS6 | Platform 2.0
C8-S3 | C8 | White-label · Headless | Integration client | P0 | Not Started | API Lead | API/Security | C1-S3 | integration_client scoped auth | Cross-tenant client denied | PRS 2.0; UXIA 2.0; DEV-002A; OpenAPI Delta 2.0 | CO-G09 | 0% | No |  | CS6 | Platform 2.0 | D2-T11
C8-S4 | C8 | White-label · Headless | Module grants | P0 | Not Started | API Lead | API/Security | C8-S3 | integration_module_grant | Only granted modules/scopes accessible | PRS 2.0; UXIA 2.0; DEV-002A; OpenAPI Delta 2.0 | CO-G09 | 0% | No |  | CS6 | Platform 2.0 | API-G08
C8-S5 | C8 | White-label · Headless | Webhook subscription | P0 | Not Started | API Lead | API/Integration | C8-S3 | webhook_subscription | Retry/idempotency/audit supported | PRS 2.0; UXIA 2.0; DEV-002A; OpenAPI Delta 2.0 | CO-G09 | 0% | No |  | CS6 | Platform 2.0 | GATE-PROD-08
C8-S6 | C8 | White-label · Headless | Headless SSO/OIDC handoff | P0 | Not Started | Security Lead | Security/API | C8-S3 | external identity binding + token validation | Server rechecks tenant/scope; no client-only trust | PRS 2.0; UXIA 2.0; DEV-002A; OpenAPI Delta 2.0 | CO-G09 | 0% | No |  | CS6 | Platform 2.0 | API-G08
C9-S1 | C9 | Contract Test · Release Gate | Run SQL contract pack | P0 | Not Started | QA/Data | QA/DB | C0-S4; C6-S5 | Execute D2-T01~T16 | DB-visible assertions pass; E2E-only not faked | DEV-002A Test Pack 2.0; Church OS MVP Acceptance Pack 1.0; DGM Handoff 1.2 | CO-G10 | 0% | No |  | CS7 | Release | D2-T01~16
C9-S2 | C9 | Contract Test · Release Gate | Run API contract gates | P0 | Not Started | QA/API | QA/API | C0-S3; C7-S6 | Execute API-G01~G10 | All BLOCKER API gates pass | DEV-002A Test Pack 2.0; Church OS MVP Acceptance Pack 1.0; DGM Handoff 1.2 | CO-G10 | 0% | No |  | CS7 | Release | API-G01~10
C9-S3 | C9 | Contract Test · Release Gate | MVP-A acceptance | P0 | Not Started | QA/Product | QA/E2E | C1-S6; C2-S7; C3-S6 | Church Core journey suite | MVP-A works without CHGO and privacy gates pass | DEV-002A Test Pack 2.0; Church OS MVP Acceptance Pack 1.0; DGM Handoff 1.2 | CO-G10 | 0% | No |  | CS7 | Release | MVP Acceptance Pack
C9-S4 | C9 | Contract Test · Release Gate | MVP-B acceptance | P0 | Not Started | QA/Product | QA/E2E | C4-S7; C5-S7 | Formation/Mission journey suite | No scoring; practice/opportunity semantics pass | DEV-002A Test Pack 2.0; Church OS MVP Acceptance Pack 1.0; DGM Handoff 1.2 | CO-G10 | 0% | No |  | CS7 | Release | MVP Acceptance Pack
C9-S5 | C9 | Contract Test · Release Gate | MVP-C acceptance | P0 | Not Started | QA/Privacy | QA/E2E | C6-S8; C7-S7 | CHGO bridge + pastor aggregate suite | Identity/privacy/evidence/suppression invariants pass | DEV-002A Test Pack 2.0; Church OS MVP Acceptance Pack 1.0; DGM Handoff 1.2 | CO-G10 | 0% | No |  | CS7 | Release | MVP Acceptance Pack
C9-S6 | C9 | Contract Test · Release Gate | Failure injection suite | P0 | Not Started | QA/SRE | QA/SRE | C6-S5; C8-S5 | L2 outage/duplicate/retry/webhook/gateway failure | Safe degraded/fail-closed behavior | DEV-002A Test Pack 2.0; Church OS MVP Acceptance Pack 1.0; DGM Handoff 1.2 | CO-G10 | 0% | No |  | CS7 | Release | CI-08
C9-S7 | C9 | Contract Test · Release Gate | UX/accessibility smoke | P0 | Not Started | QA/UX | QA/Frontend | C2-S3; C4-S7; C5-S7; C7-S7 | role/mobile/web/a11y smoke | UX acceptance passes | DEV-002A Test Pack 2.0; Church OS MVP Acceptance Pack 1.0; DGM Handoff 1.2 | CO-G10 | 0% | No |  | CS7 | Release | CI-09
C9-S8 | C9 | Contract Test · Release Gate | Release evidence report | P0 | Not Started | QA Lead | Release/Governance | C9-S1~C9-S7 | commit/migration/OpenAPI/policy/ontology/test evidence | PASS/CONDITIONAL/FAIL/NOT TESTABLE honestly reported | DEV-002A Test Pack 2.0; Church OS MVP Acceptance Pack 1.0; DGM Handoff 1.2 | CO-G10 | 0% | No |  | CS7 | Release | CI-10
C10-S1 | C10 | Open Decisions · ADR | OD-01 suppression threshold decision | P1 | Not Started | Privacy/Legal/Pilot | Governance | C0-S5 | Decision record for OD-01 | No numeric threshold hard-coded before approval | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-01 | CS0 | Governance
C10-S2 | C10 | Open Decisions · ADR | OD-02 IAM/OIDC ADR | P1 | Not Started | Security Lead | Governance | C0-S5 | Decision record for OD-02 | Provider/scopes recorded in ADR before production | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-02 | CS0 | Governance
C10-S3 | C10 | Open Decisions · ADR | OD-03 PARTIAL eligibility policy | P1 | Not Started | Growth Governance | Governance | C0-S5 | Decision record for OD-03 | Policy version controls eligibility | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-03 | CS0 | Governance
C10-S4 | C10 | Open Decisions · ADR | OD-04 retention/deletion policy | P1 | Not Started | Privacy/Legal | Governance | C0-S5 | Decision record for OD-04 | No invented retention duration | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-04 | CS0 | Governance
C10-S5 | C10 | Open Decisions · ADR | OD-05 event transport ADR | P1 | Not Started | SRE Lead | Governance | C0-S5 | Decision record for OD-05 | Transport choice does not change contract | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-05 | CS0 | Governance
C10-S6 | C10 | Open Decisions · ADR | OD-06 Raw Vault protocol | P1 | Not Started | Privacy/Security | Governance | C0-S5 | Decision record for OD-06 | No inline raw protected bridge body | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-06 | CS0 | Governance
C10-S7 | C10 | Open Decisions · ADR | OD-07 Today AI ranking decision | P1 | Not Started | Product/AI | Governance | C0-S5 | Decision record for OD-07 | Operational fallback retained | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-07 | CS0 | Governance
C10-S8 | C10 | Open Decisions · ADR | OD-08 Pastor Action routing validation | P1 | Not Started | AI/Domain | Governance | C0-S5 | Decision record for OD-08 | Recommendation provenance required | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-08 | CS0 | Governance
C10-S9 | C10 | Open Decisions · ADR | OD-09 Ontology runtime transport | P1 | Not Started | Ontology Lead | Governance | C0-S5 | Decision record for OD-09 | Canonical semantics unchanged | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-09 | CS0 | Governance
C10-S10 | C10 | Open Decisions · ADR | OD-10 data residency/hierarchy | P1 | Not Started | Platform/Security | Governance | C0-S5 | Decision record for OD-10 | Platform 2.0 decision, not MVP blocker unless jurisdiction requires | DGM Handoff 1.2 | CO-G10 | 0% | No | OD-10 | CS0 | Governance

## Lists
Status | Priority | Ready | Release Slice
Not Started | P0 | No | Foundation
In Progress | P1 | Yes | MVP-A
Blocked | P2 |  | MVP-B
Done |  |  | MVP-C
Deferred |  |  | Platform 2.0
Release
Governance

## Dashboard
Implementation Backlog 1.2 — Church OS 2.0 Delta
KPI | Value | Epic | Name | Stories | P0 | Done | Progress
Delta Stories | 77 | C0 | Handoff & Contract Freeze | 5 | 5 | 0 | 0%
P0 Stories | 65 | C1 | Church Core · People & Groups | 6 | 6 | 0 | 0%
P1 Stories | 12 | C2 | Today · Worship · Events · Content | 7 | 7 | 0 | 0%
Done | 0 | C3 | Care · Prayer · Privacy | 6 | 6 | 0 | 0%
In Progress | 0 | C4 | Formation Journey | 7 | 7 | 0 | 0%
Blocked | 0 | C5 | Mission · Serve | 7 | 7 | 0 | 0%
Overall Progress | 0% | C6 | Privacy Gateway · CHGO Bridge | 8 | 8 | 0 | 0%
|  | C7 | CHGO Response · Pastor-safe Intelligence | 7 | 7 | 0 | 0%
|  | C8 | White-label · Headless | 6 | 4 | 0 | 0%
|  | C9 | Contract Test · Release Gate | 8 | 8 | 0 | 0%
|  | C10 | Open Decisions · ADR | 10 | 0 | 0 | 0%

## Release Gates
Gate | Name | PASS Condition | Status | Owner | Evidence / Notes
CO-G01 | Source Freeze | CO-00~CO-12 versions/paths match DGM 1.2 | Not Started | Tech Lead
CO-G02 | Database | DEV-002 physical diff complete; migration repeatable | Not Started | Data Architect
CO-G03 | API | OpenAPI 3.1 parse/lint + forbidden-field lint PASS | Not Started | API Lead
CO-G04 | MVP-A Core | People/Groups/Today/Worship/Events/Content operational without CHGO | Not Started | Product/QA
CO-G05 | Care/Prayer Privacy | visibility/protected separation/audit PASS | Not Started | Privacy/Security
CO-G06 | MVP-B Formation | Formation/Mission/Serve work without maturity scoring | Not Started | Product/QA
CO-G07 | Privacy Gateway | pseudonym/purpose/consent/outbox/safety PASS | Not Started | Privacy/Security
CO-G08 | MVP-C CHGO | Candidate/Evidence + Pastor aggregate/suppression/provenance PASS | Not Started | Growth/Data/QA
CO-G09 | Headless | tenant/scope/module/webhook/SSO contract PASS | Not Started | API/Security
CO-G10 | Release | CI-01~10 + MVP Acceptance Pack yields valid release decision | Not Started | QA/Governance

## Traceability
Chain | Upstream | Implementation | Test / Gate
Product | Product Discovery → PRS 2.0 | C1~C8 tickets | GATE-PROD-01~08
UX | PRS → UXIA 2.0 | C2/C3/C4/C5/C7/C8 | UX-A01~ / UX-G01~10
Integration | PRS/UX → Integration Contract | C6/C7 | IC-T01~16; IC-G01~10
Persistence | Integration → DEV-002A Schema/ERD/SQL | C0/C1/C3/C4/C5/C6/C8 | D2-T01~16
API | Integration + Schema → OpenAPI Delta | C0/C6/C7/C8 | API-G01~10
Release | All above → Acceptance Pack | C9 | CO-G01~10
Invariant | Ticket Areas | Primary Tests
Person ≠ GrowthEpisode | C1,C6 | D2-T01; API-G02
Candidate ≠ Evidence | C7 | API-G04; IC-G03
Practice ≠ Outcome | C4,C7 | D2-T03; API-G04
Missing ≠ 0 | C7 | IC-T08
No Opportunity ≠ Failure | C4,C5 | D2-T04; IC-T07
Completion ≠ Maturity | C4 | D2-T02; UX-A04
Pastor Aggregate Only | C7 | D2-T10; API-G05
Coach Dual Gate | C6/L4 | IC cross-tests
Raw Separation | C3,C4,C6 | D2-T09; D2-T15; API-G03
No Spiritual Score | C1,C4,C5,C7 | D2-T01; release blocker
L2 Outage Independence | C2,C6 | D2-T08; API-G07
Safety Overrides Growth | C6 | IC-T16

## Open Decisions
ID | Decision | Owner Domain | Freeze Rule | Status | Linked Ticket
OD-01 | OD-01 suppression threshold decision | Privacy/Legal/Pilot | No numeric threshold hard-coded before approval | OPEN | C10-S1
OD-02 | OD-02 IAM/OIDC ADR | Security Lead | Provider/scopes recorded in ADR before production | OPEN | C10-S2
OD-03 | OD-03 PARTIAL eligibility policy | Growth Governance | Policy version controls eligibility | OPEN | C10-S3
OD-04 | OD-04 retention/deletion policy | Privacy/Legal | No invented retention duration | OPEN | C10-S4
OD-05 | OD-05 event transport ADR | SRE Lead | Transport choice does not change contract | OPEN | C10-S5
OD-06 | OD-06 Raw Vault protocol | Privacy/Security | No inline raw protected bridge body | OPEN | C10-S6
OD-07 | OD-07 Today AI ranking decision | Product/AI | Operational fallback retained | OPEN | C10-S7
OD-08 | OD-08 Pastor Action routing validation | AI/Domain | Recommendation provenance required | OPEN | C10-S8
OD-09 | OD-09 Ontology runtime transport | Ontology Lead | Canonical semantics unchanged | OPEN | C10-S9
OD-10 | OD-10 data residency/hierarchy | Platform/Security | Platform 2.0 decision, not MVP blocker unless jurisdiction requires | OPEN | C10-S10

## Source Map
ID | Artifact | Role | Backlog Impact
CO-00 | Church OS Product Discovery & Competitive Architecture 1.0 | Discovery rationale | C1~C8
CO-01 | CHGO Church OS Product Requirements Specification 2.0 | Product requirements | C1~C8
CO-02 | CHGO Church OS UX & Information Architecture 2.0 | UX/state/role/privacy | C2~C8
CO-03 | Church OS ↔ CHGO Engine Integration Contract 1.0 | L3↔L2/L4 boundary | C6,C7
CO-04 | DEV-002A Church OS Schema Delta 2.0 | Logical schema delta | C0~C8
CO-05 | DEV-002A PostgreSQL Migration Patch 2.0 | Physical migration | C0,C9
CO-06 | DEV-002A Church OS ERD 2.0 | Physical relationships | C0,C9
CO-07 | Church OS OpenAPI Delta 2.0.docx | Human API contract | C0,C6,C7,C8,C9
CO-08 | CHGO_Church_OS_OpenAPI_Delta_2.0.yaml | Machine API contract | C0,C9
CO-09 | DEV-002A Contract Test Pack 2.0 | DB/API test spec | C9
CO-10 | DEV-002A Contract Test SQL Pack 2.0.sql | DB test automation | C9
CO-11 | Church OS MVP Acceptance Test Pack 1.0 | Release test baseline | C9
CO-12 | Church OS MVP Acceptance Test Matrix 1.0.csv | Execution template | C9
DGM-1.2 | DGM Developer Handoff & Traceability Update 1.2 | Source hierarchy / CI / open decisions | C0,C9,C10